## project
Open Classes Project Planner
[7 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
| ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84
Requirements | Use Cases | 1 | 5 | 1 | 4 | 100%
| HW & SW Requirements | 2 | 5 | 1 | 3 | 100%
| Draft Document | 5 | 6 | 7 | 6 | 100%
| Other Diagrams | 5 | 10 | 7 |  | 75%
| Final Req. Document | 16 | 5 | 16 |  | 50%
| Reviews | 10 | 8 | 10 |  | 75%
| Presentation | 17 | 1 |  |  | 50%
Plan | Plan Resources | 8 | 12 | 10 | 8 | 100%
| Schedule 1 (MS Project) | 15 | 2 | 15 | 2 | 100%
| Task Network Diagram | 15 | 2 | 15 | 2 | 100%
| Risks | 15 | 2 | 15 | 2 | 100%
| Schedule 2 (MS Project) | 23 | 9 |  |  | 0%
| Reviews | 18 | 14 | 18 |  | 50%
Prototype | UID Draft | 22 | 12 |  |  | 0%
or Design / Implementation | First Prototype / High Level Design | 29 | 5 |  |  | 0%
| Reviews | 33 | 4 |  |  | 0%
| Final UID | 37 | 4 |  |  | 0%
| Final Code | 37 | 20 |  |  | 0%
Testing | Schedule | 30 | 2 |  |  | 0%
| Test Cases / Criteria | 33 | 10 |  |  | 0%
| Reviews | 43 | 8 |  |  | 0%
| Test Plan | 50 | 5 |  |  | 0%
Manual | Outline | 30 | 5 |  |  | 0%
| Screen Shots | 52 | 3 |  |  | 0%
| Preliminary User Manual | 51 | 8 |  |  | 0%
| Reviews | 56 | 6 |  |  | 0%
Presentation | Deliverables | 8 | 76 | 8 |  | 10%
| Presentation | 71 | 14 |  |  | 0%